## Main
Today | Copy this doc and follow the link below for instructions. |  | 32 |  | 21 |  |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This doc is: http://bit.ly/IGDPD_BDC_Example
2016-12-13 | http://bit.ly/IGDPD_BDC_Instructions |  | Hours | Hours | Hours |  |  | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed
Rank | Task | Assn | Est. | Worked | Rem. |  |  | 2016-12-07 | 2016-12-08 | 2016-12-09 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | Detailed Information | #
Task Assignments
| — Vehicle Physics — | [25 empty] | 5
1 | Acceleration | A | 4 | 6 | 1 |  | 4 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 6
1 | Speed | A | 2 | 2 | 1 |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 7
1 | Braking | A | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 8
1 | Turning | A | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 9
1 | Collision Implementation | H | 4 | 3 | 2 |  | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 10
11
| — Camera — | [25 empty] | 12
1 | Delayed Car Angling Tracking | G | 2 | 3 | 0 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
1 | Zoom Out When Driving | G | 1 |  | 1 |  | 1 | [19 empty] | 14 | bar: 2016-12-07 to 2016-12-21
15
| — Art — | [25 empty] | 16
3 | Art Asssets | I | 4 |  | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 17
2 | AI Driving | H | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 18
1 | Car Animation | I | 1 |  | 1 |  | 1 | [19 empty] | 19 | bar: 2016-12-07 to 2016-12-21
20
| — Gameplay & Scoring — | [25 empty] | 21
1 | Pick Up People | G | 1 |  | 1 |  | 1 | [19 empty] | 22 | bar: 2016-12-07 to 2016-12-21
3 | Risky Driving System | G | 2 | 1 | 0 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
2 | Point System | I | 2 |  | 1 |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 24
2 | Time Limit | I | 1 |  | 1 |  | 1 | [19 empty] | 25 | bar: 2016-12-07 to 2016-12-21
26
| — AI Behavior — | [25 empty] | 27
4 | AI Driving | H | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Sprint Settings – Only change cells with dark gray borders | [7 empty] | 2016-12-07: Workdays |  | 101
| Archon | A |  | Start Date | 2016-12-07 |  |  | 2016-12-07: Sun; 2016-12-08: 0; 2016-12-09: 0 |  | 102
| Henri | H |  | End Date | 2016-12-21 |  |  | 2016-12-07: Mon; 2016-12-08: 1; 2016-12-09: 1 |  | 103
| Icarus | I | [5 empty] | 2016-12-07: Tue; 2016-12-08: 1; 2016-12-09: 1 |  | 104
| Gilbert | G |  | Total Days | 14 |  |  | 2016-12-07: Wed; 2016-12-08: 1; 2016-12-09: 1 |  | 105
|  |  |  | Work Days | 10 |  |  | 2016-12-07: Thu; 2016-12-08: 1; 2016-12-09: 1 |  | 106
[8 empty] | 2016-12-07: Fri; 2016-12-08: 1; 2016-12-09: 3 |  | 107
| All | ALL | [5 empty] | 2016-12-07: Sat; 2016-12-08: 0; 2016-12-09: 0 |  | 108
| Unassigned | [25 empty] | 109
| Days to Look Back for Burndown Velocity | 2 | [24 empty] | 110
Interpreted Data – DO NOT CHANGE ANYTHING HERE | [26 empty] | 111
| Current Hours Remaining |  |  |  |  | Days | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 112
[6 empty] | On-Track Line | 32 | 32 | 28.8 | 25.6 | 22.4 | 19.2 | 16 | 12.8 | 9.6 | 6.4 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 113
114
[6 empty] | Sum | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 115
| Rank (and not reduced to 0 after today) | [25 empty] | 116
| Rank 1 - The MOST important | 1 |  |  |  | Rank 1 | 19 | 17 | 14 | 13 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 |  | 117
|  | 2 |  |  |  | Rank 2 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 118
|  | 3 |  |  |  | Rank 3 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 119
|  | 4 |  |  |  | Rank 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 120
| Rank 5 - The LEAST important | 5 |  |  |  | Rank 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 121
[6 empty] | Sum | 32 | 30 | 27 | 26 | 25 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 |  | 122
123
[6 empty] | Archon | 10 | 9 | 9 | 8 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | 124
[6 empty] | Henri | 8 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | 125
[6 empty] | Icarus | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 |  | 126
[6 empty] | Gilbert | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 127
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 128
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 129
[6 empty] | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 130
[6 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 131
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 133
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134
135
[5 empty] | Team | 4 | [20 empty] | 136
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  | 137
[6 empty] | Average Assigned | 8 | 7.5 | 6.75 | 6.5 | 6.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 |  | 138
[6 empty] | On-Track Line | 8 | 8 | 7.2 | 6.4 | 5.6 | 4.8 | 4 | 3.2 | 2.4 | 1.6 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 139
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 140
141
[7 empty] | 2016-12-06 | 2016-12-07 | 2016-12-08 | 2016-12-09 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 |  | 142
| Total Hours | 32 | [5 empty] | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 143
| Hours 2 Days Ago | 26 |  |  |  |  | 32 | 30 | 27 | 26 | 25 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 |  | 144
| Hours Today | 21 |  |  |  | Burndown Velocity |  |  |  | 26 | 23.5 | 21 | 18.5 | 16 | 13.5 | 11 | 8.5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | 145
| Today | 6 |  |  |  | BDV | 2016-12-06: 2.5 |  | 146
147
148
149
150

## Daily Scrum
2016-12-13 |  | Team Members
Dates |  | Archon | Henri | Icarus | Gilbert | Workday
2016-12-07 | Wed | Yesterday: Project Kickoff Today: Acceleration Help: – Nothing now | Yesterday: Project Kickoff Today: Collisions Help: – | Yesterday: Project Kickoff Today: I'm out of town until 12/13 Help: – | Yesterday: Project Kickoff Today: No time today H: – | 1
2016-12-08 | Thu | Y: About 25% of Accel T: – Not able to work today H: – | Y: Collisions about 25% done T: More collisions H: – | Y: – T: Still out of town. Call if you need anything (555) 867-5309. H: – | Y: – T: Follow cam (delayed car angling tracking thing) H: – | 1
2016-12-09 | Fri | Y: – T: Acceleration tuning H: Something feels wrong about the acceleration. I could use some help. | Y: Collisions at about 50% now T: I have a little time to help Archon H: – | Y: – T: – H: – |  | 1
2016-12-10 | Sat |  |  |  |  | 0
2016-12-11 | Sun |  |  |  |  | 0
2016-12-12 | Mon | Y: (Fri) Got help from Henri with acceleration. It's at about 50% now. T: Speed management. H: – | Y: Didn't do any of my work because Acceleration issues took all my time. T: – Out for the next three days H: – | Y: – T: Back tomorrow. H: – |  | 1
2016-12-13 | Tue | Y: Speed 50% complete T: More accel; hopefully finishing. H: – |  | Y: – T: Finally back! Working on Point System. H: If someone could help get me back up to speed, I'd appreciate it. | Y: – T: Risky driving system H: – | 1
2016-12-14 | Wed |  |  |  |  | 1
2016-12-15 | Thu |  |  |  |  | 1
2016-12-16 | Fri |  |  |  |  | 1
2016-12-17 | Sat |  |  |  |  | 0
2016-12-18 | Sun |  |  |  |  | 0
2016-12-19 | Mon |  |  |  |  | 1
2016-12-20 | Tue |  |  |  |  | 1
2016-12-21 | Wed |  |  |  |  | 1
2016-12-22 | Thu |  |  |  |  | 1
2016-12-23 | Fri |  |  |  |  | 1
2016-12-24 | Sat |  |  |  |  | 0
2016-12-25 | Sun |  |  |  |  | 0
2016-12-26 | Mon |  |  |  |  | 1
2016-12-27 | Tue |  |  |  |  | 1
2016-12-28 | Wed |  |  |  |  | 1